NoDrftSystems

SOP Library

Standard Operating Procedures

Version 1.0 | April 2026

Internal Operations Document

# SOP Inventory

| SOP | Purpose | Owner | Required Outputs |
| --- | --- | --- | --- |
| SOP-001: Intake | Keep funnels separate | Growth/Qualification Lead | Routed inquiry + response template |
| SOP-002: Qualification | Fit screening + package routing | Growth Lead + Founder | Recommended package + next step |
| SOP-003: Discovery Sprint | Clarify scope before build | Founder + UX/Content Lead | Scope brief + package recommendation |
| SOP-004: Build Execution | Bounded delivery with defined outputs | Implementation Lead | Build plan + deliverables checklist |
| SOP-005: QA Multi-Pass | Package integrity + language + pricing + proof | ARE + specialists | QA checklist + fix list |
| SOP-006: Release | Human sign-off release discipline | ARE + Founder | Completion report + sign-off record |
| SOP-007: Careers | Continuous but controlled talent intake | Growth Lead | Triage result + applicant record |
| SOP-008: Contractor Onboarding | Add specialists without losing control | Founder + ARE | SOW + access controls + QA rules |

# SOP-001: Intake

Purpose: Keep funnels separate (Inquiries vs Start an Engagement)

Owner: Growth/Qualification Lead

Trigger: New inquiry received

Outputs: Routed inquiry + response template

## Overview

This SOP ensures inquiries are properly categorized and routed to the appropriate workflow. The key distinction is between project intake (Start an Engagement) and general inquiries.

## Steps

Receive inquiry via website form, email, or referral

Categorize: Project inquiry vs General inquiry vs Partnership

For project inquiries: Route to Start an Engagement form

For general inquiries: Log and respond within 24 hours

For partnerships: Flag for Founder review

## Decision Tree

Does the inquiry mention a specific project, timeline, or budget? → Route to Start an Engagement. Is it general contact, media, or partnership? → General inquiry path. Is it unclear? → Respond asking for clarification.

# SOP-002: Qualification

Purpose: Fit screening + package routing

Owner: Growth Lead + Founder

Trigger: Completed Start an Engagement form

Outputs: Recommended package + next step

## Overview

This SOP ensures every prospect is evaluated against fit criteria before proposal. The Client Evaluation Scorecard is mandatory.

## Steps

Review completed Start an Engagement form

Score against Client Evaluation Scorecard (minimum 75/100)

Identify red flags (vague scope, unallocated budget, >3 decision makers)

Determine recommended package based on scope

Apply risk pricing multipliers if needed

Prepare proposal or decline with referral

## Decision Matrix

| Score | Action |
| --- | --- |
| 90-100 | High priority - fast-track proposal |
| 75-89 | Standard proposal process |
| 60-74 | Discovery Sprint required |
| Below 60 | Politely decline with referral |

# SOP-003: Discovery Sprint

Purpose: Clarify scope before build

Owner: Founder + UX/Content Lead

Trigger: Discovery Sprint contracted

Outputs: Scope brief + package recommendation

## Overview

This SOP governs the Discovery Sprint delivery to ensure scope clarity before build commitment.

## Steps

Schedule 2-hour discovery workshop with client

Pre-workshop: Send questionnaire (business objectives, constraints, stakeholders)

Workshop: Facilitate structured discussion covering objectives, users, content, technical requirements

Document: Create scope brief within 48 hours

Review: Present scope brief to client for validation

Recommend: Propose appropriate package and timeline

## Deliverables

Scope brief document (business context, objectives, requirements, constraints)

Execution plan (phases, timeline, dependencies)

Package recommendation with pricing

# SOP-004: Build Execution

Purpose: Bounded delivery with defined outputs

Owner: Implementation Lead

Trigger: Contract signed, deposit received

Outputs: Build plan + deliverables checklist

## Overview

This SOP governs the build phase to ensure on-scope, on-time delivery with quality outcomes.

## Steps

Kickoff: Schedule client kickoff call, confirm scope and timeline

Plan: Create detailed build plan with milestones

Build: Execute with AI-augmented production, ARE validation at each milestone

Review: Present work at each milestone for client feedback

Revise: One round of revisions included; additional billed separately

Finalize: Complete all deliverables per checklist

## Milestone Structure

M1: Design approval (wireframes/mockups)

M2: Development checkpoint (50% complete)

M3: Content integration

M4: QA and refinement

M5: Final approval and handoff

# SOP-005: QA Multi-Pass

Purpose: Package integrity + language + pricing + proof

Owner: ARE + specialist reviewers

Trigger: Build complete, ready for review

Outputs: QA checklist + fix list

## Overview

This SOP ensures comprehensive quality review across multiple dimensions before release.

## Review Passes

### 1. Package Integrity Review

Ladder matches commercial offer

Inclusion/exclusion frames present

Upgrade logic shown

'From' used only with real variability

### 2. Plain Language Review

No acronyms dropped cold

Glossary covers key terms

Buyer-safe explanations on-page

### 3. Pricing Safety Review

Only approved figures appear

Exclusions visible

No bait pricing

### 4. Public-Proof Review

Controlled snapshots

Confidentiality safe

No client names unless approved

### 5. Bilingual Review

Meaning, tone, CTA strength parity

Transcreation quality

### 6. Accessibility Review

Headings, labels, forms

WCAG 2.2 baseline compliance

# SOP-006: Release

Purpose: Human sign-off release discipline

Owner: ARE + Founder

Trigger: All QA passes complete

Outputs: Completion report + sign-off record

## Overview

This SOP ensures fail-closed release gates are passed before any public deployment.

## Release Gates

| Gate | Question | Proceed Only If... |
| --- | --- | --- |
| Strategic | Does this match the business objective? | Brief satisfied without scope drift |
| Factual | Are claims verified or clearly labeled? | Unsupported claims removed or flagged |
| Operational | Can the output be used immediately? | Required fields, files, instructions complete |
| Disclosure | Does it protect confidentiality and IP? | No prohibited internals exposed |
| Consistency | Is it coherent across sections and locales? | Terminology, hierarchy, logic all match |
| Testing | Was it validated against defined targets? | Relevant checks run and logged |
| Human Sign-off | Is human approval required? | ARE or designated reviewer has approved |

## Steps

ARE completes QA checklist and fix list

ARE generates completion report

Founder reviews completion report

Founder approves release (PROCEED) or requests changes (HOLD)

If PROCEED: Deploy to production

If HOLD: Return to build with specific fix requirements

# SOP-007: Careers

Purpose: Continuous but controlled talent intake

Owner: Growth Lead

Trigger: Application received

Outputs: Triage result + applicant record

## Overview

This SOP ensures careers remains live continuously while maintaining selectivity and privacy.

## Steps

Receive application via careers form

Acknowledge receipt within 48 hours

Categorize: Active role applicant vs Future opportunity vs Specialist interest

For active roles: Review against job requirements, schedule interview if qualified

For future opportunities: Add to talent pool, contact when role opens

For specialists: Evaluate portfolio/experience, add to vetted bench

Maintain applicant records for 24 months

# SOP-008: Contractor Onboarding

Purpose: Add specialists without losing control

Owner: Founder + ARE

Trigger: Specialist identified and vetted

Outputs: SOW + access controls + QA rules

## Overview

This SOP ensures specialists are onboarded with clear boundaries and quality controls.

## Steps

Identify need for specialist expertise

Source from vetted bench or new referral

Review portfolio/work samples

Execute professional services contract (not employment)

Define SOW: scope, deliverables, timeline, payment terms

Set up access controls (limited to specific project)

Communicate QA rules and review gates

ARE validates all deliverables before client delivery

## Contract Requirements

Multiple clients clause (contractor free to serve others)

Deliverables-based payment (not hourly/salary)

No exclusivity requirement

Contractor provides own equipment

No fixed hours (results-oriented)

# SOP Template

Use this template for creating new SOPs.

SOP Name: [Name]

Purpose: [One-line description of what this SOP accomplishes]

Owner: [Role responsible for this SOP]

Trigger: [What initiates this SOP]

Inputs (Required): [What is needed to execute this SOP]

Steps (Bounded):

1) [Step 1]

2) [Step 2]

3) [Step 3]

Outputs (Definition of Done): [What constitutes completion]

Review Gates Required: [What approvals are needed]

Records Produced: [Where are outputs stored]

Escalation Conditions: [When to escalate to Founder]